1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting authority

Mnicipality of trgovište

## Country background

1.3.	Country background

The cross-border region, comprising the municipalities of Trgovište and Kostinbrod, is characterized by sufficient water resources, but they are in poor ecological condition due to pollution - domestic and production, poorly strengthened troughs, which ruin and raise the water level and threaten the infrastructure in the settlements. There is a lack of targeted action to develop policies in both municipalities with regard to environmental prevention, management and monitoring and the reduction of the consequences of natural and man-made disasters - heavy rains in the autumn-winter season, river beds, landslides, pollution with domestic waste, illegal logging in vulnerable areas, etc.

The current state of affairs is complemented by the lack of awareness and awareness among the population of the importance of civic consciousness for the protection of the environment and the preservation of natural resources.

Activities under this project are designed to overcome these limitations in effective environmental management, monitoring and prevention. By developing common action plans for environmental management and monitoring and disaster protection, prevention and prognosis, an approach for long-term co-operation will be implemented and will lay the foundations for future activities and measures between the two municipalities. Acquired specialized equipment will respond directly to the needs of the responsible institutions by available response techniques during floods and other disaster situations and thus to the needs of the population. The trainings will raise awareness and support the implementation of environmental policies that will have a positive impact on the quality of life in the region in the long run and the increased environmental awareness of citizens will help municipal institutions in their environmental management.

## Current situation in the sector

erbia has developed a completely new set of laws and strategies in the field of environmental protection… despite several changes in the state structure since the 2002 review. It is making serious efforts to approximate national legislation to EU environmental legislation.

A number of laws have been adopted, such as the Law on Environmental Protection, the Law on Environmental Impact Assessment (EIA), the Law on Strategic Environmental Assessment (SEA) and the Law on Integrated Pollution Prevention and Control (IPPC); other laws on waste, noise and biodiversity are awaiting adoption by the National Assembly. In addition, many strategies have been adopted since 2002. In 2006, the government adopted the National Environmental Protection Strategy, which is now awaiting a decision by the National Assembly.

The project contributes to the improvement of communal infrastructure in Trgovište and environmental protection, as well as the protection of the Pčinja River and the prevention of pollution of the river. The objectives are: protection of the Pčinja river from pollution and preservation of water quality through efficient collection and treatment of waste. Improving the level of municipal services through the development of municipal infrastructure and improving the quality of life. Promotion of the Municipality of Trgovište as a very clean environment and the utilization of natural potentials of the Pčinja River for the development of tourism. Promoting the Trgovište municipality as an extremely suitable municipality for the production of healthy food. The project contributes to capacity building, information exchange, training and ad hoc support that will assist project partners for full preparation and application in cross-border projects. Overall objective: Contribution to cross-border social and economic integration through further building and promotion of partnerships based on the preparation and application of joint projects of local governments in the cross-border region. Specific objective: Capacity building of employees in local administrations in the cross-border districts of Pčinja and Pernik, through establishment of partnership and training for more efficient preparation and implementation of joint projects. The project contributes to achieving the objectives of the Territorial Cooperation Strategy in the area of climate change and environmental risks, as well as the Europe 2020 Strategy and the Common Strategic Framework. The project has a direct contribution to the national strategy for the management and development of the water sector and in particular to objective 4. Reducing the risk of flood damage. The implementation of the planned activities will contribute to Priority 3 of the National Development Program: Bulgaria 2020 and in particular the vision for improving the quality of life in rural areas, effective and sustainable management of natural resources. The project supports the achievement of SO 3: Risk management of natural disasters - floods, landslides, etc. of the Regional Strategy for Development of the Sofia Region 2014-2020 as well as of the SO 2, Measure 2.2.2: Rational management and use of water resources and preservation of their purity in the Municipal Development Plan of the Municipality of Kostinbrod 2014-2020 and Objective 3.2: Improved and built infrastructure for protection and protection of the environment, meeting the EU standards Strategy for sustainable development of the Municipality of Targovište 2010-2020

## Related programmes and other donor activities

N/A

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

The project aims at the joint implementation of intelligent policies for management, monitoring and protection of the environment in the cross-border region of the municipalities of Targovishte and Kostinbrod

## Purpose

The purpose of this contract is as follows:

- To organize events of the project on quality manner to satisfy intervention logic, parameters for outputs and adequate budget requirements.

## Results to be achieved by the contractor

- Hall rented for conducting joint theoretical and tactical exercises and field training for emergency management

- Hall rented for joint training and awareness-raising of public service stakeholders and population for disaster resilience

- Hall rented for Training volunteers for action in disasters and crises

- Audio/video equipment rented for conducting joint theoretical and tactical exercises and field training for emergency management

-	Audio/video equipment rented for joint training and awareness-raising of public

service stakeholders and population for disaster resilience

-	Audio/video equipment rented for Training volunteers for action in disasters and crises

-     Bus rented for travel to Kostinbrod for conducting joint theoretical and tactical

exercises and field training for emergency management (20 participants)

- Bus rented for travel to Kostinbrod for joint training and awareness raising of public service stakeholders and population for disaster resilience (20 participants)

- Bus rented for travel to Kostinbrod for Training volunteers for action in disasters and crises (20 participants)

- Catering provided for conducting joint theoretical and tactical exercises and field training for emergency management for 40 participants (coffee, refreshment, lunch and dinner for 3 days)

- Catering provided for joint training and awareness raising of public service stakeholders and population for disaster resilience for 40 participants (coffee, refreshment, lunch and dinner for 3 days)

- Catering provided for Training volunteers for action in disasters and crises for 40 participants (coffee, refreshment, lunch and dinner for 2 days)

- Accommodation provided for 20 Serbian participants in the conducting joint theoretical and tactical exercises and field training for emergency management - 2 nights

- Accommodation provided for 20 Serbian participants in the joint training and awareness raising of public service stakeholders and population for disaster resilience - 2 nights

- Accommodation provided for 20 Training volunteers for action in disasters and crises - 1 night

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

N/A

## Risks

N/A

# SCOPE OF THE WORK

## General

### Description of the assignment

Rent of hall for conducting joint theoretical and tactical exercises and field training for emergency management

Rent of hall for joint training and awareness-raising of public service stakeholders and population for disaster resilience

Rent of hall for Training volunteers for action in disasters and crises

Renting audio/video equipment for conducting joint theoretical and tactical exercises and field training for emergency management

Renting audio/video equipment for joint training and awareness-raising of public service stakeholders and population for disaster resilience

Renting audio/video equipment for Training volunteers for action in disasters and crises

Rent of bus for travel to Kostinbrod for conducting joint theoretical and tactical exercises and field training for emergency management (20 participants)

Rent of bus for travel to Kostinbrod for joint training and awareness raising of public service stakeholders and population for disaster resilience (20 participants)

Rent of bus for travel to Kostinbrod for Training volunteers for action in disasters and crises (20 participants)

Catering for conducting joint theoretical and tactical exercises and field training for emergency management for 40 participants (coffee, refreshment, lunch and dinner for 3 days)

Catering for joint training and awareness raising of public service stakeholders and population for disaster resilience for 40 participants (coffee, refreshment, lunch and dinner for 3 days)

Catering for Training volunteers for action in disasters and crises for 40 participants (coffee, refreshment, lunch and dinner for 2 days)

Accommodation for 20 Serbian participants in the conducting joint theoretical and tactical exercises and field training for emergency management - 2 nights

Accommodation for 20 Serbian participants in the joint training and awareness raising of public service stakeholders and population for disaster resilience - 2 nights

Accommodation for 20 Training volunteers for action in disasters and crises - 1 night

### Geographical area to be covered

CBC targeted area of Trgovište (Serbia) and Kostinbrod (Bulgaria)

### Target groups

Stakeholders of the projects

## Specific work

Contractor will organize following events:

1. Joint theoretical and tactical exercises and field training for emergency management

Contractor will provide all managerial, organization, logistic, visibility and protocol activities according to description in the list of specific activities. For every activity Contractor will achieve parameter of acceptability mentioned in relevant column of the list, especially ones connected with time limits and quantities and qualities of goods and services.

Place of training- Trgovište ± 20 km

Duration of the training 3 days

Number of participants 40 (20 from Serbia and 20 from Bulgaria)

Time of performance – 5th – 7th trimesters

Detailed of the tasks needs

| Task | Description | Time | Parameter of acceptability |
| --- | --- | --- | --- |
| Accommodation of participants | Contractor will organize accommodation for 20 participants in 2-bed rooms (bed separated) with bathrooms in the hotels with 3*, for 2 nights. Buffet breakfast included. | Accommodation reserved minimum 1 week before training | On time and in accordance with specification and pandemic regulations |
| Renting a hall | Booking of adequate space in Trgovište and equipment at least 10 days before the event. Space will be equipped with enough seats for at least 40 persons, tables for equipment and lecturers. Space will be adequate tempered (20-22 0C) due to season of training performance. Contractor will provide space for coffee break, catering and for work of logistic staff and media. Hall must be organized in the accordance with COVID-19 pandemic rules of the Serbian government. Contractor will decorate the provided space with visibility material (rollups, banners, posters, photos) if such is provided by Project team. | 10 day before training and during the training | On time and in accordance with specification and pandemic regulations |
| Rent a presentation equipment | Contractor will provide audio/visual equipment for the rented space to ensure that lecturers and participants will see PPP and heard each other. Also, contractor will provide one flip chart. Contractor will install and proof all necessary equipment for work (video projecting system, lights, computers, tables and seats). Also, contractor will provide persons for the equipment manipulation. | 1 day before training and during the training |  |
| Providing refreshment and catering | Catering for conducting joint theoretical and tactical exercises and field training for emergency management for 40 participants (coffee, refreshment, lunch and dinner for 3 days). Contractor will provide coffee and refreshment on training breaks and catering and non-alcoholic beverages for lunch and dinner During each day of training will be 3 breaks and quantity of coffee and refreshment will be: 3 x 3 x 40 coffee = 360 Refreshment juices 3 x 3 x 40 x 0.25 l = 90 l Two meals will be served per day/per participant (lunch and dinner). Meals should contain: soup (200 ml/person), 2 main courses (1 with meat, 1 without meat, with side dish – 450gr/person), salad (50gr/person), dessert (50gr/person), sparkling and still mineral water (500ml/person), soft drink (500 ml/person), coffee with milk and sugar (1 piece/person), bread, with possibilities that meals would be served in the training space out of hotel. Also, 20% of meals would be for vegetarians. In the case that lunch will be served out of hotel, Consultant will provide foods that will include: - At least 10 different finger foods, - At least 2 different sweets, - At least 2 vegetarian finger foods - All necessary equipment (plastic cups, forks, knives, serviettes and similar) | Detailed menu prepared week before training | On time, and in accordance with specification and pandemic regulations |

2. Joint training and awareness-raising of public service stakeholders and population for disaster resilience

Contractor will provide all managerial, organization, logistic, visibility and protocol activities according to description in the list of specific activities. For every activity Contractor will achieve parameter of acceptability mentioned in relevant column of the list, especially ones connected with time limits and quantities and qualities of goods and services.

Place of training- Trgovište ± 20 km

Duration of the training 3 days

Number of participants 40 (20 from Serbia and 20 from Bulgaria)

Time of performance – 5th – 7th trimesters

Detailed of the tasks needs

| Task | Description | Time | Parameter of acceptability |
| --- | --- | --- | --- |
| Accommodation of participants | Contractor will organize accommodation for 20 participants in 2-bed rooms (bed separated) with bathrooms in the hotels with 3*, for 2 nights. Buffet breakfast included. | Accommodation reserved minimum 1 week before training | On time and in accordance with specification and pandemic regulations |
| Renting a hall | Booking of adequate space in Trgovište and equipment at least 10 days before the event. Space will be equipped with enough seats for at least 40 persons, tables for equipment and lecturers. Space will be adequate tempered (20-22 0C) due to season of training performance. Contractor will provide space for coffee break, catering and for work of logistic staff and media. Hall must be organized in the accordance with COVID-19 pandemic rules of the Serbian government. Contractor will decorate the provided space with visibility material (rollups, banners, posters, photos) if such is provided by Project team. | 10 day before training and during the training | On time and in accordance with specification and pandemic regulations |
| Rent a presentation equipment | Contractor will provide audio/visual equipment for the rented space to ensure that lecturers and participants will see PPP and heard each other. Also, contractor will provide one flip chart. Contractor will install and proof all necessary equipment for work (video projecting system, lights, computers, tables and seats). Also, contractor will provide persons for the equipment manipulation. | 1 day before training and during the training |  |
| Providing refreshment and catering | Catering for conducting joint theoretical and tactical exercises and field training for emergency management for 40 participants (coffee, refreshment, lunch and dinner for 3 days). Contractor will provide coffee and refreshment on training breaks and catering and non-alcoholic beverages for lunch and dinner During each day of training will be 3 breaks and quantity of coffee and refreshment will be: 3 x 3 x 40 coffee = 360 Refreshment juices 3 x 3 x 40 x 0.25 l = 90 l Two meals will be served per day/per participant (lunch and dinner). Meals should contain: soup (200 ml/person), 2 main courses (1 with meat, 1 without meat, with side dish – 450 gr/person), salad (50gr/person), dessert (50 gr/person), sparkling and still mineral water (500 ml/person), soft drink (500 ml/person), coffee with milk and sugar (1 piece/person), bread, with possibilities that meals would be served in the training space out of hotel. Also, 20% of meals would be for vegetarians. In the case that lunch will be served out of hotel, Consultant will provide foods that will include: - At least 10 different finger foods, - At least 2 different sweets, - At least 2 vegetarian finger foods - All necessary equipment (plastic cups, forks, knives, serviettes and similar) | Detailed menu prepared week before training | On time, and in accordance with specification and pandemic regulations |

3. Training volunteers for action in disasters and crises

Contractor will provide all managerial, organization, logistic, visibility and protocol activities according to description in the list of specific activities. For every activity Contractor will achieve parameter of acceptability mentioned in relevant column of the list, especially ones connected with time limits and quantities and qualities of goods and services.

Place of training- Trgovište ± 20 km

Duration of the training 2 days

Number of participants 40 (20 from Serbia and 20 from Bulgaria)

Time of performance – 5th – 7th trimesters

Detailed of the tasks needs

| Task | Description | Time | Parameter of acceptability |
| --- | --- | --- | --- |
| Accommodation of participants | Contractor will organize accommodation for 20 participants in 2-bed rooms (bed separated) with bathrooms in the hotels with 3*, for 1 night. Buffet breakfast included. | Accommodation reserved minimum 1 week before training | On time and in accordance with specification and pandemic regulations |
| Renting a hall | Booking of adequate space in Trgovište and equipment at least 10 days before the event. Space will be equipped with enough seats for at least 40 persons, tables for equipment and lecturers. Space will be adequate tempered (20-22 0C) due to season of training performance. Contractor will provide space for coffee break, catering and for work of logistic staff and media. Hall must be organized in the accordance with COVID-19 pandemic rules of the Serbian government. Contractor will decorate the provided space with visibility material (rollups, banners, posters, photos) if such is provided by Project team. | 10 day before training and during the training | On time and in accordance with specification and pandemic regulations |
| Rent a presentation equipment | Contractor will provide audio/visual equipment for the rented space to ensure that lecturers and participants will see PPP and heard each other. Also, contractor will provide one flip chart. Contractor will install and proof all necessary equipment for work (video projecting system, lights, computers, tables and seats). Also, contractor will provide persons for the equipment manipulation. | 1 day before training and during the training | On time and in accordance with specifications contracted |
| Providing refreshment and catering | Catering for conducting joint theoretical and tactical exercises and field training for emergency management for 40 participants (coffee, refreshment, lunch and dinner for 2 days). Contractor will provide coffee and refreshment on training breaks and catering and non-alcoholic beverages for lunch and dinner During each day of training will be 3 breaks and quantity of coffee and refreshment will be: 2 x 3 x 40 coffee = 240 Refreshment juices 2 x 3 x 40 x 0.25 l = 60 l Two meals will be served per day/per participant (lunch and dinner). Meals should contain: soup (200 ml/person), 2 main courses (1 with meat, 1 without meat, with side dish – 450 gr/person), salad (50 gr/person), dessert (50 gr/person), sparkling and still mineral water (500 ml/person), soft drink (500 ml/person), coffee with milk and sugar (1 piece/person), bread, with possibilities that meals would be served in the training space out of hotel. Also, 20% of meals would be for vegetarians. In the case that lunch will be served out of hotel, Consultant will provide foods that will include: - At least 10 different finger foods, - At least 2 different sweets, - At least 2 vegetarian finger foods - All necessary equipment (plastic cups, forks, knives, serviettes and similar) | Detailed menu prepared week before training | On time, and in accordance with specification and pandemic regulations |

4. Bus transportation for 20 persons on the relation Trgovište-Kostinbrod-Trgovište.

Contractor will provide adequate touristic bus for transportation 20 persons from Trgovište on the following events that will perform at Kostinbrod and after the end of events return them to Trgovište:

4.1 Joint theoretical and tactical exercises and field training for emergency management (20 participants). Event will have duration of 3 days

4.2 Joint training and awareness raising of public service stakeholders and population for disaster resilience (20 participants). Event will have duration of 3 days

4.3 Rent of bus for travel to Kostinbrod for Training volunteers for action in disasters and crises (20 participants). Event will have duration of 2 days.

Buses will be at least 5 years old, equipped as standard touristic bus air conditioners, with all licences and permits to cross state boundaries, drive by experienced crew.

## Project management

### Responsible body

Responsible body will be Project team of the Municipality of Trgovište

### Management structure

Responsible person will be Project manager

### Facilities to be provided by the contracting authority and/or other parties

Contracting authority will provide agenda of trainings to the Contractor

# LOGISTICS AND TIMING

## Location

Municipality of Trgovište and Kostinbrod.

## Start date & period of implementation of tasks

The intended start date is 13.04.2021. and the period of implementation of the contract will be 12 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.<.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and 1 copy:

- Inception Report (interim report 1) to be produced after 1 month from the start of implementation. In the report the contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report.

- Interim report II after completed 2 3-days trainings.

Final report after completing 1 2 days training.

## Submission and approval of reports

The reports referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

The reports will be will be accompanied by adequate invoice

# MONITORING AND EVALUATION

## Definition of indicators

Indicators will be parameters of acceptability

## Special requirements

N/A